## Working route
Blackboard Group No 39 Class ZDD | Project Planning |  |  |  |  | Version 1 |  |  |  |  | Version 2 (optional) |  |  |  |  | Version 3 (option) |  |  |  |  | Last Chance Submission
SMART goals ==> | Specific tasks and WBS | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING TESTING (not) DONE DONE LATE HUNG UP | Specific tasks and WBS | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING TESTING (not) DONE DONE LATE HUNG UP | Specific tasks and WBS | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING TESTING (not) DONE DONE LATE HUNG UP | Specific tasks and WBS | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING TESTING (not) DONE DONE LATE HUNG UP | Specific activities | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING TESTING (not) DONE DONE LATE HUNG UP
reference and relative due dates | Reference Date: July 25, 2023 Relative Due Dates: 1. Research and outline: Due on July 27, 2023 (2 days from the reference date) 2. First draft: Due on July 30, 2023 (5 days from the reference date) 3. Review and revisions: Due on August 2 , 2023 (7 days from the reference date) 4. Final submission: Due on August 6, 2023 (11 days from the reference date) | Update E3 to your PM class date | =====> | 2023-07-25 |  | Reference Date: July 25, 2023 Relative Due Dates: 1. Research and outline: Due on July 27, 2023 (2 days from the reference date) 2. First draft: Due on July 30, 2023 (5 days from the reference date) 3. Review and revisions: Due on August 1 , 2023 (6 days from the reference date) 4. Final submission: Due on August 6, 2023 (11 days from the reference date) | All agreements have been made | PM class date plus | 9 | days |  |  | PM class date plus | 14 | days |  |  | PM class date plus | 21 | days | Latest possible submission is last day of classes; late penalties apply at 20% per day after your Version 3 due date: | august 13 , 2023 Sunday
Each Team member | Your Project Mgmt notes on what each Process Group means to you when doing this project. | Share with team by uploading PM-Notes-myName.docx to Bb 39 team channel's Files |  | Wednesday Jul.26 | DONE | Each team member Developing a secure authentication system involves planning, backend and frontend development, testing, UX improvement, and clear documentation. It aims to provide a user-friendly experience while ensuring data security and efficient user role management. | see Programming Comments and Programming Test Cases docs for acceptance criteria. See Project Overview - Appendix B for deliverables |  | Wednesday July 26 | DONE | Each team member Developing a secure authentication system involves planning, backend and frontend development, testing, UX improvement, and clear documentation. It aims to provide a user-friendly experience while ensuring data security and efficient user role management. | see Programming Comments and Programming Test Cases docs for acceptance criteria. See Project Overview - Appendix B for deliverables |  |  | DONE | Each team member Developing a secure authentication system involves planning, backend and frontend development, testing, UX improvement, and clear documentation. It aims to provide a user-friendly experience while ensuring data security and efficient user role management. | see Programming Comments and Programming Test Cases docs for acceptance criteria. See Project Overview - Appendix B for deliverables |  | 2023-08-11 | DONE
Team Meeting Agenda ==> | create MS Teams Private Channel; for Version 1, create plan with SMART goals and assign tasks | detailed tasks assigned to Team members with est. hrs., agreed upon delivery date to Teams, updated Status | 1.5 |  | DONE | Project progress is evaluated by comparing work which is completed, actual hours spent on that particular module, and tehn we both discussed the collected from the team and stakeholders. Based on this assessment, estimates of the remaining work are refined and the project schedule is adjusted. The final delivery date/time will be determined in consultation with the team and stakeholders, and the updated schedule will be communicated to all relevant parties. | In MS Team Channel, select any file you would like reviewed and send a message @instructor to comment on that file. | 2 |  | DONE | Team decision whether to do this version. If so, members plan to complete V2 of their module. | detailed tasks assigned to Team members with est. hrs., agreed upon delivery date/time to Teams, updated Status |  |  | DONE | Team decision whether to do this version. If so, members plan to complete V3 of their module. | detailed tasks assigned to Team members with est. hrs., agreed upon delivery date/time to Teams, updated Status | 2.5 hrs |  | DONE | Submit final version of artefacts from Teams to Blackboard in a .ZIP archive. Backup Team's files. | updated all DONE items with actual hours. |  | aug 13 2023 Sunday | DONE
| request review from professor | Request review of this file: see Project Milestones and Details page, "Request review of a file..." |  | Sunday july 30 | DONE | request review from professor | Request review of this file: see Project Milestones and Details page, "Request review of a file..." |  | Sunday July 30 | DONE | request review from professor | Request review of this file: see Project Milestones and Details page, "Request review of a file..." |  |  | DONE | request review from professor | Request review of this file: see Project Milestones and Details page, "Request review of a file..." |  |  | DONE |  |  |  |  | DONE
Drashti Desai Fundamentals | Review each other's PM notes on process Teams. Agree on how project will be done. Decide which module to do & choose Team Leader | Completeness:The delivereable is evaluated to ensure that all the agrred-upon features and components are implement and integrated as exepted. | 1 | Thursday 27 july | DONE | This includes the implementation of the Fundamental module, which focuses on string . The main work in this is wrinting a function which combines the strings,by taking the user input for both the first and second strings, and if the input is 'q' then it exits, and also prints the concatenated string. Finally,after testing and debugging program it is necessary to ensure that the module functions correctly funtioning and provides the results correctly. | Deliverable is measured by successfully implementing the Fundamental module for string fundamention. work here includes like writing a function to concatenate strings, handling user input, checking for 'q' to quit, printing the concatenated string, and conducting thorough testing and debugging. Agreement on delivery criteria is essential for defining success. | 2 | Thursday July 27 | DONE | The project's progress assessment involves carrying out the "Fundamental" module, which emphasizes the core aspects of string manipulation. The primary sub-assignments entail developing a function for string concatenation, handling user inputs for the first and second strings, validating the input 'q' for exit, and displaying the merged string. Lastly, comprehensive testing and thorough debugging are imperative to ensure the module functions accurately and delivers the desired results. | The attainment of deliverables is assessed through the successful execution of the "Foundational" module for string fundamentation. Subtasks encompass developing a function to merge strings, managing user input, validating 'q' for termination, displaying the merged string, and undertaking comprehensive testing and meticulous debugging. It is vital to establish a consensus on delivery standards to define the project's triumph. | 3 HRS | 7 AUG , TUESDAY | DONE | The project's progress assessment involves carrying out the "Fundamental" module, which emphasizes the core aspects of string manipulation. The primary sub-assignments entail developing a function for string concatenation, handling user inputs for the first and second strings, validating the input 'q' for exit, and displaying the merged string. Lastly, comprehensive testing and thorough debugging are imperative to ensure the module functions accurately and delivers the desired results. | The attainment of deliverables is assessed through the successful execution of the "Foundational" module for string fundamentation. Subtasks encompass developing a function to merge strings, managing user input, validating 'q' for termination, displaying the merged string, and undertaking comprehensive testing and meticulous debugging. It is vital to establish a consensus on delivery standards to define the project's triumph. | 2.5hr |  | DONE |  |  |  | aug 13 2023 Sunday | DONE
Ali Naraghi Manipulations | Review each other's PM notes on process Teams. Agree on how project will be done. Decide which module to do & choose Team Leader | Performance: The performance of the deliverable is assessed in terms of speed, responsiveness, and efficiency. It should meet the predefined performance benchmarks. | 1 | Thursday 27 july | DONE | This includes the implementation of the "Manipulation" module, which focuses on string manipulation. The main subtasks include writing a function to concatenate strings, handling user input for the first and second strings, checking input 'q' for exit, and printing the concatenated string. Finally, thorough testing and debugging is necessary to ensure that the module functions correctly and provides the desired results. | The Manipulation module's success is measured by its correct implementation for string manipulation, including the work like concatenating strings, handling user input, checking for 'q' to exit, and printing the result. Agreement on delivery criteria is important to define success. | 2 | saturday July 29 | DONE | The project involves the execution of the "Manipulation" module, which centers on string handling. The primary subassignments comprise crafting a function to merge strings, managing user inputs for the initial and secondary strings, validating the input 'q' for termination, and displaying the combined string. Lastly, comprehensive testing and meticulous debugging are vital to guarantee the accurate functioning of the module, delivering the intended outcomes. |  | 2.5 hrs | 7 aug , TUESDAY | DONE | The project involves the execution of the "Manipulation" module, which centers on string handling. The primary subassignments comprise crafting a function to merge strings, managing user inputs for the initial and secondary strings, validating the input 'q' for termination, and displaying the combined string. Lastly, comprehensive testing and meticulous debugging are vital to guarantee the accurate functioning of the module, delivering the intended outcomes. |  | 2 hrs | 12 aug Saturday | DONE |  |  |  | aug 13 2023 Sunday | DONE
Ali Naraghi Tokenizing | Review each other's PM notes on process Teams. Agree on how project will be done. Decide which module to do & choose Team Leader | Quality: The quality of the deliverable is gauged by checking for bugs, defects, and adherence to coding standards and best practices. | 1 | 4 august Friday | DONE | The main work here involves implementing the Tokenizing module with working on the other things like writing a function to tokenize words, handling user input for words, checking for 'q' input to quit, printing tokens (words), and performing testing and debugging to ensure the module functions correctly. | Deliverable is measured by successfully implementing the Tokenizing module for word tokenization. work included writing a function for tokenizing words, handling user input, checking for 'q' to quit, printing tokens, and conducting testing and debugging. Agreement on delivery criteria is essential for defining success. | 2.5 | 4 august Friday | DONE | The assignment entails executing the 'Tokenizing' component with subassignments such as creating a function to break down words into tokens, managing user inputs for words, verifying 'q' input for termination, displaying the tokens (words), and conducting thorough testing and meticulous debugging to ascertain the module operates accurately. |  | 3.5hrs | 7 AUG , TUESDAY | DONE | The assignment entails executing the 'Tokenizing' component with subassignments such as creating a function to break down words into tokens, managing user inputs for words, verifying 'q' input for termination, displaying the tokens (words), and conducting thorough testing and meticulous debugging to ascertain the module operates accurately. |  | 3 hrs | 12 aug Saturday | DONE |  |  |  | aug 13 2023 Sunday | DONE
Drashti Desai Conversions Team Leader | Review each other's PM notes on process Teams. Agree on how project will be done. Decide which module to do & choose Team Leader | User Experience: The deliverable's UX is evaluated to ensure it provides a positive and intuitive user experience, focusing on ease of use and user satisfaction. | 1 | Sunday 6 august | DONE | The main work here is implementing the Converting module with work like writing a program to Convert words, handl ing user input for words, checking for 'q' input to quit, printing convert (words), and performing testing and debugging to ensure the module functions correctly. | Deliverable is measured by successfully implementing the Converting module for word conversion. work include writing a function to convert words, handling user input, checking for 'q' to quit, printing converted words, and conducting testing and debugging. Agreement on delivery criteria is essential for defining success. | 1.5 | Sunday 6 august | DONE | The project entails executing the 'Converting' module with subassignments such as devising a function to Transform words, managing user inputs for words, validating 'q' input for termination, displaying the converted (words), and undertaking comprehensive testing and thorough debugging to guarantee the module operates accurately. | The success of this project hinges on the effective implementation of the 'Converting' module for word transformation. Key responsibilities involve developing a function to convert words, managing user input, detecting the termination command 'q,' displaying the transformed words, and conducting thorough testing and debugging. Ensuring mutual understanding and alignment on the delivery standards is crucial for determining triumph in this endeavor. | 2.5hrs | 8 aug wedusday | DONE | The project entails executing the 'Converting' module with subassignments such as devising a function to Transform words, managing user inputs for words, validating 'q' input for termination, displaying the converted (words), and undertaking comprehensive testing and thorough debugging to guarantee the module operates accurately. | The success of this project hinges on the effective implementation of the 'Converting' module for word transformation. Key responsibilities involve developing a function to convert words, managing user input, detecting the termination command 'q,' displaying the transformed words, and conducting thorough testing and debugging. Ensuring mutual understanding and alignment on the delivery standards is crucial for determining triumph in this endeavor. | 2.5 hrs | 2023-08-13 | DONE |  |  |  | aug 13 2023 Sunday | DONE
|  |  |  | milestone upload to Blackboard |  |  |  |  | milestone upload to Blackboard | DONE |  |  |  | milestone upload to Blackboard | DONE |  |  |  | DUE DATE upload to Blackboard | DONE |  |  |  | ABSOLUTE DEADLINE
[7 empty] | What is the team's criteria for acceptance of development (files on developer's PC) when promoted to integration (Files in team's channel) What file names? What is definition of done / good enough? Who decides that? Project Overview and Programming Comments¦Testing docs have this information to be quoted or referenced. Requests for professor's review come after the team has accepted the work. |  | saturday July 30 | DONE | [8 empty] | submissions after this date subject to extra time charge of 20% per day |  |  |  |  | no submissions accepted after this date
Note on A1: Update ?? to your Blackboard group number and XYY to your CPR101XYY class code. Then press TAB to next set up item in E3.
Note on A2: Use SMART goals to achieve the Triple Constraint of Cost/Resource vs Time/Schedule vs Scope/Quality.
Note on B2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on C2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on D2: How many hours will the task take?
Note on E2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on F2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: work in progress: an objective or task according to a Time based target – hours of effort will be completed by a due date & time TESTING: work promoted by team member after Doing to other team members for Testing/Measurement. DONE: an objective or task Tested/Measured as completed. Only Team leader can change status to DONE (or back to DOING for rework or HUNG UP for problem resolution) HUNG UP: no longer doing something because it became unRealistic. Tell the team right away. E.g. hours required will not be completed by the due date-time; specific objectives were found to be too vague when Doing; no metrics were applied to measure doneness.
Note on G2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on H2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on I2: How many hours will the task take?
Note on J2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on K2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: work in progress: an objective or task according to a Time based target – hours of effort will be completed by a due date & time TESTING: work promoted by team member after Doing to other team members for Testing/Measurement. DONE: an objective or task Tested/Measured as completed. Only Team leader can change status to DONE (or back to DOING for rework or HUNG UP for problem resolution) HUNG UP: no longer doing something because it became unRealistic. Tell the team right away. E.g. hours required will not be completed by the due date-time; specific objectives were found to be too vague when Doing; no metrics were applied to measure doneness.
Note on L2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on M2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on N2: How many hours will the task take?
Note on O2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on P2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: work in progress: an objective or task according to a Time based target – hours of effort will be completed by a due date & time TESTING: work promoted by team member after Doing to other team members for Testing/Measurement. DONE: an objective or task Tested/Measured as completed. Only Team leader can change status to DONE (or back to DOING for rework or HUNG UP for problem resolution) HUNG UP: no longer doing something because it became unRealistic. Tell the team right away. E.g. hours required will not be completed by the due date-time; specific objectives were found to be too vague when Doing; no metrics were applied to measure doneness.
Note on Q2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on R2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on S2: How many hours will the task take?
Note on T2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on U2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: work in progress: an objective or task according to a Time based target – hours of effort will be completed by a due date & time TESTING: work promoted by team member after Doing to other team members for Testing/Measurement. DONE: an objective or task Tested/Measured as completed. Only Team leader can change status to DONE (or back to DOING for rework or HUNG UP for problem resolution) HUNG UP: no longer doing something because it became unRealistic. Tell the team right away. E.g. hours required will not be completed by the due date-time; specific objectives were found to be too vague when Doing; no metrics were applied to measure doneness.
Note on V2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on W2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on X2: How many hours will the task take?
Note on Y2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on Z2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: work in progress: an objective or task according to a Time based target – hours of effort will be completed by a due date & time TESTING: work promoted by team member after Doing to other team members for Testing/Measurement. DONE: an objective or task Tested/Measured as completed. Only Team leader can change status to DONE (or back to DOING for rework or HUNG UP for problem resolution) HUNG UP: no longer doing something because it became unRealistic. Tell the team right away. E.g. hours required will not be completed by the due date-time; specific objectives were found to be too vague when Doing; no metrics were applied to measure doneness.
Note on E3: Change this to the date of your Project Management class and the worksheet will calculate all milestone dates.